## V5 Template
HREiR Action plan template |  | Must read prior to completing action plan
Following an update to the HREiR Award action plan in 2026 you are now required to map actions in your plan to a minimum of 6 obligations and at least one from each pillar (Environment and Culture, Employment and Professional and Career Development). In your summary report you will have confirmed what those obligations will be by assessing what change you want to see in the next 3 years and from this analysis you will pick what obligations align with those desired changes. In the action plan below please add your chosen obligations from the 'Obligations tab' and complete the action plan.
Action plan timeline: | 2026/27 to 2028/29
Institution name: | University of Lancashire
Cohort number: | Cohort 6
Date of submission: | 2026-05-01
| Obligation | Action to be taken during three year cycle to support obligation | Carried over from previous action plan? | What will success look like? | Expected Impact of this Action for your plans audience (please include Research only staff (Concordat priority audience)) | Deadline | Responsibility
| include the overall obligation and sub obligations | the number of actions you choose to include per Obligation is at your insitutions discretion |  | progress and impact will be measured through SMART objectives, supported by clear KPIs, metrics, and feedback mechanisms
Environment and Culture
Awareness and engagement
1A | Ensure all relevant staff are aware of the Concordat and that institutional policies and practices related to researchers are inclusive, equitable, and transparent. | YEAR 1: Deliver School/Institute events on Concordat and wider support for research development, initially targetting new Schools; Medicine and Dentistry, and Veterinary Medicine. | Yes | ~ Delivery of two targeted events (or series of short sessions) for School of Medicine and Dentistry, and Veterinary Medicine ~ Increased awareness of Concordat measured from CEDARS (or equivalent) and session evaluations - 80% of research staff in Schools are aware of the Concordat and where to find support. | ~ Increased staff morale. ~ Increased research metrics associated with this group (publications, involvment in bidding, participation in events). | 2027-07-01 | Academic Development for Research & Knowledge Exchange
1A | Ensure all relevant staff are aware of the Concordat and that institutional policies and practices related to researchers are inclusive, equitable, and transparent. | YEAR 2: Deliver School/Institute events on Concordat and wider support for research development, targetting areas of low participation in training and development. | Yes | ~ Delivery of targeted event (or series of short sessions) for three Schools/Institutes. ~ Increased participation at School and University level in centrally coordinated events, training and surveys. 10% increase yoy in Researcher Development activities. ~ Increased awareness of Concordat measured from CEDARS (or equivalent) - 80% of research staff in Schools are aware of the Concordat and where to find support. | ~ Increased staff morale. ~ Increased research metrics associated with this group (publications, involvment in bidding, participation in events). | 2028-07-01 | Academic Development for Research & Knowledge Exchange
1A | Ensure all relevant staff are aware of the Concordat and that institutional policies and practices related to researchers are inclusive, equitable, and transparent. | YEAR 3: Deliver School/Institute events on Concordat and wider support for research development,targetting areas not included in YEAR 1 and YEAR 2. | Yes | ~ Delivery of targeted event (or series of short sessions) for other school/institute that are not included in Years 1 &2 ~ Increased participation at School and University level in centrally coordinated events, training and surveys. 10% increase yoy in Researcher Development activities. ~ Increased awareness of Concordat measured from CEDARS (or equivalent) | ~ Increased staff morale. ~ Increased research metrics associated with this group (publications, involvment in bidding, participation in events). | 2029-07-01 | Academic Development for Research & Knowledge Exchange
1A | Ensure all relevant staff are aware of the Concordat and that institutional policies and practices related to researchers are inclusive, equitable, and transparent. | Improve researcher participation in development activities by establishing network of ECR and MCR leads to shape programme of events, activities and resources. | No | ~ECR and MCR Champions to identify development needs and jointly design sessions to support career development. The sessions will cover the Researcher Concordat, the Technician Commitment, and other relevant concordats and policies. ~ ECR and MCR Champions help shape the Concordat themed sessions, and we can clearly see their ideas reflected in the researcher development offer (measured by the number of Concordat sessions where ECR/MCR Champions were involved in planning or topic selection). ~ 80% positive response on relevance of activity measured by session feedback and follow up survey, and CEDARS. ~ More researchers take part and come back for future sessions, with better understanding of the Concordat (10% increase in attendance yoy, 80% positive responses in session feedback). | ~ Researchers feel more heard and involved, which helps build trust and encourages more people to get involved. ~ Development activities feel more relevant and useful for ECRs and MCRs, making career development part of everyday research life. | 2028-07-01 | Academic Development for Research & Knowledge Exchange
1A | Ensure all relevant staff are aware of the Concordat and that institutional policies and practices related to researchers are inclusive, equitable, and transparent. | ADRKEs will work with ECRs to co create an ECR Charter that clearly sets out how we support Early Career Researchers. It will outline the support, opportunities and expectations for ECRs, and how schools and the wider institution will work together to create a positive research environment. | No | ~ ECRs are involved in shaping the ECR Charter, and their ideas can clearly be seen in the final document and how it’s used (measured from regular reviews of the Charter with ECR input built into the process) ~ Staff across the institution know about the Concordat and the ECR Charter and have a shared understanding of how ECRs should be supported day to day (measured by percentage of relevant staff who report awareness of the Concordat and ECR Charter in CEDARS). ~ The ECR Charter is easy to find and understand, clearly setting out what ECRs can expect and what support schools and the institution will provide (measured from ECR feedback confirming the Charter is clear and easy to understand). ~ Evaluation at end of Year 3 will assess progress - 80% ECRs agree that positive changes to research culture have been achieved. | ~ ECRs feel clearer and more confident about the support, opportunities and expectations that come with their roles. ~ The institution can clearly show its commitment to the Concordat and to creating a positive, inclusive research culture. | 2027-07-01 | Academic Development for Research & Knowledge Exchange
Equality, diversity and inclusion
4A | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion (EDI), and put this into practice in their work. | Develop programme of activity and resources to support EDI-related aspects of research via our Research and Knowledge Exchange for all (RKE4All) programme - to be based on findings of report due summer 2026 | No | ~ RKE4All conference held in July 2026. Evaluation to measure baseline and provide opportunity for feedback from the community. ~ RKE4All EDI Leads recommendations produced - July 2026. Priority actions agreed based on this report - September 2026. ~ Awareness of RKE4All framework - Measured from CEDARS (or equivalent) ~ Attendance at RKE4All events - (Measured from session evaluation). ~ Consultation with the working group of ECRs, MCRs and Senior researchers aorund this programme of activity. | ~ ~ The RKE4ALL EDI Leads’ recommendations help turn ideas about inclusion into clear, practical actions. ~ More people know about the RKE4All framework and understand how it helps make research and knowledge exchange fairer and more inclusive. ~ Higher attendance at RKE4All events shows growing interest and confidence in getting involved with EDI activity. ~ Research is more inclusive. | July 2027 | RKE4All Leads & Academic Development for Research & Knowledge Exchange
4A | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Develop and roll out programme of unconscious bias training for REF2029 decision makers | No | ~ 100% of staff with decision making responsibilities in REF2029 undertake unconscious bias training - (Measured from session evaluation). | ~ People involved in REF2029 decisions are aware of bias and feel more confident spotting and calling it out when it happens. ~ REF related decisions are fairer and more consistent; with less chance that bias affects the outcome. ~ The REF2029 process feels clearer, showing a commitment to fairness and inclusion. | 2028-07-01 | REF Team
4A | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Ensure that REF2029 preparation is inclusive through regular Equality Impact Assessments and monitoring of participation across the exercise. | Yes | ~ Participation across REF2029 preparations will be monitored annually by protected characteristic, including participation in events, nomination exercises, and within REF volume measure. ~ Equality Impact Assessment is updated annually and action plan progress reviewed by RKE EDI Group three times per annum. ~ CEDARS evaluation (or equivalent) to assess researcher views on inclusivity of REF2029 preparations. ~ 80% of research staff participate in annual output nomination exercise. 100% of research staff are aware of the REF. 10% yoy increase in page views for REF information. | ~ REF2029 prep is fairer and more inclusive because potential issues are picked up early and checked regularly, not just at the end. ~ Who’s taking part in REF decisions is looked at over time, helping make sure no groups are missed or left out. ~ Any issues flagged through the Equality Impact Assessment are followed up, building confidence that the REF process is being handled openly and fairly. | 2028-07-01 | REF Team
Research Integrity
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Update the current Policy for Research Misconduct in align with the UK Research Integerity Office Guidance (Detailed Template Procedure for Investigating Breaches of Research Integrity December 2025) and the Concordat to Support Research Integrity (2025). | No | ~ Procedure for Investigating Potential Breaches of Research Integrity in place. Approved by the Research Knowledge Exchange Governance Sub Committee. Published and communicated to staff and students. ~ >80% awareness of research integrity processes and procedures in CEDARS. | ~ Clearer, more accessible procedure for preventing and addressing potential breaches of research integrity. Increased staff and student awareness of processes. | 2026-09-01 | Ethics, Integrity and Governance Unit
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Review and relaunch Code of Conduct for Research. | No | ~ Revised Code of Conduct for Research in place. Approved by the Research Knowledge Exchange Governance Sub Committee. Published and communicated to staff and students. ~ >80% awareness of research integrity processes and procedures in CEDARS. | ~ Clearly defined standards of integrity and research conduct across disciplines. | 2026-12-01 | Ethics, Integrity and Governance Unit
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Promote uptake of the UK Research Integrity Office online training (Introduction to Research Integrity, Ethics of Research Involving Human Participants. | No | ~ Training completion monitored and reported to the Research Knowledge Exchange Governance Sub-Committee ~ >50% uptake in training by end of HREiR review period. | ~ Increased knowledge and understanding of research integrity. More consistent research practices across the University. | 2026-12-01 | Ethics, Integrity and Governance Unit
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Evaluate training impact and researcher reflection. | No | ~ Survey and qualitive feedback. Findings reviewed and used to inform improvements. ~ 50% participation rate in survey achieved across all Schools. | ~ Improved understanding of how training influences researcher practice. | 2028-12-01 | Ethics, Integrity and Governance Unit
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Strengthen leadership responsbility for research integrity | No | ~ Evidence of reseach integrity communications and discussions within Schools and Research and Knowledge Exchange Institutes. | ~ Increased visibility of research integrity at leadership level. Stronger local ownership of good research practice. | 2028-12-01 | Ethics, Integrity and Governance Unit
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Enhance mechanisms for raising concerns with potential research integrity breaches. | No | ~ Updated Procedure for Investigating Potential Breaches of Research Integrity in place. Revised webpages and intranet guidance clearly outlining reporting routes and support. ~ 50% of researchers are aware of reporting procedures (CEDARS) | ~ Improved visability and accessibiliy of reporting mechanisms. Increased staff and student awareness and confidence in reporting concerns. Contribution to a more open and supportive research culture. | 2027-12-01 | Ethics, Integrity and Governance Unit
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Develop and deliver training programme for researchers on the use of artifical intelligence across the research project lifecycle. | No | ~ PLANS IN DEVELOPMENT - specifics of activity to be developed. ~ Introduce a Best Practice Guidance to support use of AI by researchers. ~ Deliver training on the ethical and responsible use of AI (3 sessions per annum). ~ Develop researcher specific workshops in a tiered way over the next 12-24 months as both technologies and researchers advance. ~ Provide forums for sharing practice and facilitating discussions on the use of AI by researchers. Number and scope tbc. ~ Measured by the attendance at training & development events, number of research misconduct cases related to AI, as well as the confidence of the research community in using AI tools (survey). | ~ Ethical and responsible use of AI by our research community. | 2029-07-01 | Centre for Collaborative Learning/Academic Development for Research & Knowledge Exchange
Employment
Recognition, reward and promotion
8A | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Create Researcher of the Month campaign to raise the profile of researchers and research across the University. | No | ~ Researchers are regularly highlighted and celebrated, with lots of interest and engagement from across the University. (Measured by the number of researchers featured each year and views) ~ Over time, many different researchers are featured, reflecting a mix of roles, disciplines and career stages. (Measured by representation across different schools, disciplines and research roles). ~ The campaign becomes well known and positive, with people looking forward to each feature and putting others forward for recognition. (Measured from staff feedback showing the campaign is recognised and viewed positively; including evaluation of experiences of those featured). | Researchers feel noticed and appreciated for their work, which boosts confidence and motivation. Research across the University is easier to see, understand and connect with. The campaign brings people together around research and encourages more interest in celebrating what researchers do. | 2027-07-01 | Academic Development for Research & Knowledge Exchange
8A | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Run annual RKE awards event to recognise research achievements across career stages and disciplines. | No | ~ The awards run every year and attract strong interest. (Measured by nomination numbers and evaluation of nomineeds, judges and attendees). ~ Researchers from across the University are recognised. (Measured by representation across career stages (ECR, MCR, CPR) and schools/research roles). ~ The awards are valued and visible across the University. (Measured by feedback showing researchers value the recognition). | Researchers feel noticed and appreciated for their achievements, which helps boost confidence at all career stages. Research from different disciplines is more visible and celebrated across the University. The awards bring people together, helping build a supportive research community where colleagues take pride in each other’s work. | July 2027 July 2028 July 2029 | Academic Development for Research & Knowledge Exchange
| Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Run annual Dragons' Den event to promote and support commercialisation by our research students and staff. | No | ~ Research staff are keen to take part and pitch their ideas. (Measured by proposal numbers, attendance at the event in person or online). ~ Participants find the event helpful, encouraging and easy to engage with. (Measured by post event feedback from participants). ~ Ideas don’t stop at the event and are signposted into further support. (Measured by the number of ideas progressing after the event; and improvement in disclosure rates). | Research staff feel more confident giving commercial ideas a go. The University feels more open to innovation and enterprise. | July 2027 July 2028 July 2029 | IP & Commercialisation Team
| Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Promote the use of Narrative CVs across Schools and Services, including training and resources. | No | ~ More people across Schools and Services know what a Narrative CV is and when to use one. (Measured by session feedback showing increased awareness or understanding). ~ Narrative CVs start to be used more widely and consistently across different Schools. (Measured by evidence of Narrative CVs being referenced in funding or development support). | Researchers and staff feel more comfortable talking about all their skills and experience, not just papers or numbers. There is a more joined up and consistent way of looking at research achievements across Schools. | July 2027 July 2028 July 2029 | Academic Development for Research & Knowledge Exchange
Job security
11A | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | Create and promote skills register to enable staff with capacity to be employed on short-term, short-notice research projects. | No | ~ Year 1 - We have a clear, up to date register of part time and/or fixed term research staff who want to take on short term or ad hoc work to build their skills and experience. ~ Years 2 and 3 - The register is actively used, with at least 10 successful matches each year between researchers and short term research opportunities. ~ Measured by: Number of people listed on register, increasing use of register to fill short term research work, number of successful matches made each year, feedback from researchers and project leads about whether the matches were useful. | This helps improve job security by making better use of the skills we already have, instead of bringing in external people or offering only short‑term contracts. Improves support effective use of short-term, short-notice funding. For research‑only staff, this means: ~ More chances to keep working between contracts or alongside their current role. ~ Better awareness of their skills and experience across the organisation. ~ Opportunities to try different projects, build confidence, and learn new skills. ~ Reputation and network building. ~Institution improves skills retention, with associated cost savings. | July 2027 July 2028 July 2029 | Academic Development for Research & Knowledge Exchange/People Team
11A | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | Run annual promotion of NW British Academy ECR Network to relevant staff. | No | ~ ECRs from relevant disciplines are signed up to the network. ~ ECRs are attending a range of events ~ ECRs are applying to BA to organise local events. ~ A range of channels are used to promote network, including other RKES teams, intranet, newsletters and events. ~ Measured by increased awareness of network in CEDARS, increased membership and attendance at events | ~ By promoting the ECR Network, this helps researchers feel more supported, better connected, and more aware of opportunities outside their day‑to‑day role. Over time, this can really help build confidence and improve job security. For research‑only staff, this means: ~Easier access to peer support, mentoring, and learning from others. ~More awareness of career options, funding, and development opportunities ~Stronger professional connections that could lead to future projects or jobs. ~ More confidence and a clearer idea of what their next career steps could be. | July 2027 July 2028 July 2029 | Academic Development for Research & Knowledge Exchange
11A | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | Assess best practice in sector in terms of support for research precarity and progression for research only staff. | No | ~ We will understand what other organisations are doing to support research only staff, especially around job security, career progression, and short term contracts to support our organisation learning on this subject. ~ We will identify good practice and report to senior colleagues what’s making a difference elsewhere. ~ We will identify ideas or approaches that can practically be implemented in our University. ~ The learning shapes next steps, such as changes to guidance, pilots of new approaches, or updates to existing support for researchers. ~ Measured by: Attendance of team at Vitae best practice events; routinely capturing examples of good practice; standing item on Researcher Development SG to report on sector practice; annual report to RKEEC on key emerging themes. | ~This helps us improve job security by learning from what’s already working well in other organisations, instead of trying to solve these issues on our own. ~ For research only staff, this should lead to: More focus on the realities of short term contracts and how they affect careers. ~ Better decisions about things like redeployment, career progression, and use of fixed term contracts. ~ Researchers feel listened to and can see steps being taken to address the issues they face. | 2028-07-01 | Academic Development for Research & Knowledge Exchange
11A | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | Roll out initiatives developed in 2024/25 to address precarity and support the grade progression of Research-Only staff. | Yes | The new initiatives to reduce precarity and support grade progression are up and running across the organisation. ~ Research only staff know about them and understand how to access them. ~Researchers are actively using the support that’s been put in place. ~ Managers understand what’s available and feel more confident using it to support researchers’ progression. ~ Measured by: Number of research only staff who take part in each initiative; feedback from researchers who have used the support. | ~ It is clearer how to move up grades and progress in their career. ~ There is better support when projects end or when moving between roles. ~ Researchers feel more confident that they can progress, when they are on fixed term contracts. ~ There is a sense that the organisation understands research precarity and is doing something practical to improve it. ~Lower turnover of research only staff leads to better skills retention, and cost savings associated with employment and training. | 2029-07-01 | Academic Development for Research & Knowledge Exchange
Professional and Career Development
Diverse careers
16A | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | Introduce new "Commercial Mindset" accelerator that trains ECRs and MCRs on how to translate research into commercial assets. |  | ~ Commercial Mindset accelerator is up and running, and researchers are joining in and finding it useful. ~ 10 early and mid career researchers complete the three week programme each year. ~ 80% participants have a better understanding of how commercialisation works by the end of the programme. ~ At least 3 academics go on to actively develop a commercial idea or proposal, such as a business case or spin out. | ~ Staff feel more positive and motivated because their ideas and skills are recognised and supported ~ Staff feel confident about trying out new career options linked to commercial work. ~ Staff have more chances to turn their research into something real‑world, whether that’s income, impact, or a business idea. For the organisation, this means: - More income coming from research ideas and intellectual property. ~ Better results for HEIF and KEF over time. ~ A research community that feels more confident and comfortable thinking about commercial possibilities. | 2028-07-01 | IP & Commercialisation Unit
16B | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | Promote University's mentoring scheme for research across ECR and MCR community. |  | ~ Early and mid career researchers know about the Uuniversity’s mentoring scheme and get involved. ~ 10 academics complete the mentoring programme each year. ~ Researchers from different backgrounds and career stages are taking part. ~ Evaluation demonstrates that the programme has supported personal and professional development. Measured by: Number of early and mid career researchers who sign up each year; Programme feedback survey; Improved staff morale, as measured by CEDARS. | ~ Staff have better sense of belonging, because they feel supported and valued (something we should see reflected in CEDARS and staff surveys). ~ Staff feel that there is a more positive and supportive research culture within the organisation. ~A stronger culture of mentoring and development across the University for research staff will be created. | 2028-07-01 | Academic Development for Research & Knowledge Exchange

## Audience
The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
Audience (direct beneficiaries of the action plan) | Number of | Comments
ECRs | 100 | ECRs and MCRs are principle beneficiaries of activites outlined in the action plan.
MCRs | 260 | ECRs and MCRs are principle beneficiaries of activites outlined in the action plan.
Academic research population | 500

## Obligations list
Environment and Culture
Obligation 1 | Awareness and engagement
1A | Ensure all relevant staff are aware of the Concordat and that institutional policies and practices related to researchers are inclusive, equitable, and transparent.
1B | Regularly review and improve the research environment and culture by seeking feedback from researchers and implementing changes based on the findings.
Obligation 2 | Wellbeing and mental health
2A | Promote good mental health and wellbeing through the effective management of workloads and people.
2B | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health and promote a healthy working environment that supports researchers' wellbeing and mental health.
Obligation 3 | Bullying and harassment
3A | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues.
3B | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment.
Obligation 4 | Equality, diversity and inclusion
4A | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work.
Obligation 5 | Research Integrity
5A | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. And that all members of staff use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct.
Obligation 6 | Policy development
6A | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making.
6B | Encourage managers and researchers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution.
Employment
Obligation 7 | Recruitment and induction
7A | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices.
7B | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position.
Obligation 8 | Recognition, reward and promotion
8A | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances.
Obligation 9 | Responsibilities and reporting
9A | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder.
Obligation 10 | People management
10A | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent.
10B | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care.
10C | Managers actively engage in regular constructive performance management with their researchers.
Obligation 11 | Job security
11A | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress.
Professional and Career Development
Obligation 12 | Championing professional development
12A | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors.
Obligation 13 | Career development reviews
13A | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers.
13B | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually.
Obligation 14 | Career development support and planning
14A | Ensure that researchers have access to professional advice on career management, across a breadth of careers.
Obligation 15 | Research identity and leadership
15A | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills.
15B | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development.
Obligation 16 | Diverse careers
16A | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this.
16B | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments.

## Example - 6 obligations added
HREiR Action plan template |  | Must read prior to completing action plan
Following an update to the HREiR Award action plan in 2025 you are now required to map actions in your plan to a minimum of 6 obligations and at least one from each pillar (Environment and Culture, Employment and Professional and Career Development). In your summary report you will have confirmed what those obligations will be by assessing what change you want to see in the next 3 years and from this analysis you will pick what obligations align with those desired changes. In the action plan below please add you chosen obligations from the 'Obligations tab' and complete the action plan.
Action plan timeline:
Institution name:
Cohort number:
Date of submission:
Please feel free to remove & add rows for your chosen obligations as appropriate
| Obligation | Action to be taken during three year cycle to support obligation | Carried over from previous action plan? | What will success look like? | Expected Impact of this Action for your plans audience (please include Research only staff (Concordat priority audience)) | Deadline | Responsibility
| include the overall obligation and sub obligations | the number of actions you choose to include per Obligation is at your insitutions discretion |  | progress and impact will be measured through SMART objectives, supported by clear KPIs, metrics, and feedback mechanisms
Environment and Culture
Wellbeing and mental health
2A | Promote good mental health and wellbeing through the effective management of workloads and people.
2B | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health and promote a healthy working environment that supports researchers' wellbeing and mental health.
Equality, diversity and inclusion
4A | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work.
Employment
People management
10A | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent.
10B | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care.
10C | Managers actively engage in regular constructive performance management with their researchers.
Professional and Career Development
Championing professional development
12A | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors.
Career development support and planning
14A | Ensure that researchers have access to professional advice on career management, across a breadth of careers.
Research identity and leadership
15A | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills.
15B | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development.